## Instructions
ELEGANCY |  |  | RISK ASSESSMENT TOOL
A. INTRODUCTION
Project | ELEGANCY - Enabling a low-carbon economy via hydrogen and CCS
an ERA-Net Cofund ACT project
About | ERA-Net ACT is a pan-European co-funding programme targeting the acceleration of the deployment of CCS technologies. The ELEGANCY project specifically aims at enabling a low-carbon economy via hydrogen and CCS. It consists of the development of design tools and business case methodologies for a fully integrated H2-CCS chain and will provide innovative, cutting edge solutions to key technical and commercial challenges for H2-CCS chains. The project includes five national case studies covering Norway, the UK, The Netherlands, Germany and Switzerland. More information is available on the project website: www.sintef.no/elegancy
B. IMPORTANT GUIDANCE
Objective | 1. To carry out a Preliminary assessment of the investment barriers and business risks for each of the business opportunities of any case study. 2. To steer the development of the appropriate business model, and to define and prioritise the actions to be taken in order to mitigate and manage those risks.
Structure | * 3 x Guidance sheets (orange): "Instructions" (objectives, general structure and overall methodology), "Detailed Instructions" (detailed instructions to fill in operating sheets) and "Risk Categories" (specific table describing risk categories and sub-categories). * 1 x General Input Sheet (brown): "Overview Information" (sheet to enter user and project/case study info). * 4 x Operating Sheets (red): "Policitical, Policy and Social", "Technical and Physical", "Market and Commercial", and "Outcome"Risk (sheets to complete the assesment of major business risks and identification of investment barriers).
Methodology | * Firstly, general information on the case study/project is input in to the general input sheet 'Overview Information' (brown). This is designed to facilitate the recording and tracking of each of the risk assessments - different versions by different respondents, and at different stages of the project * Secondly, the risk assessment is completed in the 4 assessment sheets (red). The risk assessments for the H2-CCS chain is undertaken at two levels in no particular order and with a consistency check between the two. Investment barriers can be extracted from the analysis of the major business risks or investment barriers can be identified immediately using existing knowledge of the industry and later cross-checked when the business risks have been analysed. 1. BUSINESS RISKS: IDENTIFICATION AND ASSESSMENT WITH INVESTABILITY IMPACT in the bottom table (light blue) of the assessment sheets, specific business risks affecting each of the business opportunities are identified and assessed along with their impact on the investability of the opportunity. Mitigation measures are identified/proposed and their impact on investability is quantified. The key risks are identified using four main categories: Political/Policy and Social, Technical and Physical, Market and Commercial, Outcome. These categories and additional subcategories are defined and explained in the guidance tab 'Risk Categories'. The likelihood and impact of those risks on the feasibility or value of the business opportunity are assessed using a traditional risk matrix methodology. The likelihood and impact risk rating values and descriptions are provided in the guidance tables in tab 'Detailed Instructions', and a degree of flexibility in interpretation is allowable for the severity of the impact depending on the nature of the proposed investment or operational entity. These risks impact the investability from an investor's point of view. This impact is quantified using a scale from 1 to 5 where 1 is low risk and 5 is prohibitive risk (i.e no investment is possible). Mitigation measures for cause and consequence are identified using a bow tie approach, which addresses control and recovery actions for cause and consequence respectively. 2. INVESTMENT BARRIERS In the top table (dark blue) of the assessment sheets, major investment barriers are identified. These barriers are circumstances or "facts" that raise the risk of detrimental investment outcomes to an unacceptable level for any type of investor (investability rating of 5). Generally, these barriers will affect investment in multiple segments along the chain, or the whole chain, and require a “system view” and multi-party (often in collaboration with government) approach to mitigation measures. These barriers need to be addressed in priority for any investment to be possible. These barriers can either be extracted from the business risk table (i.e from the risks with a 5 rating) or from existing knowledge given a number of these barriers have been experienced by CCS projects and commercialisation programmes, and many have been well documented. Mitigation measures need to be identified to enable public and/or private sector entities to invest and operate. This is designed to help understanding and communication of the key issues preventing investment and facilitate the engagement with the government on the actions to be taken to remove such barriers. A market failure such as a missing market is an example of an investment barrier. A regulation or statute resulting in an uncapped liability for a business is another. 3. CONSISTENCY STEP The impact of the business risks on investability in the business opportunity is also assessed from a chain perspective to determine if investment barriers and mitigations need to be reviewed and revised or the nature of the business entity needs to be modified. A consistency check between the investment barriers in the top table and the business risks in the bottom table is undertaken to ensure any business risks that result in a chain investability impact of rating 5 are escalated to an investment barrier and dealt with accordingly. Consistency between mitigation measures is also cross-checked.
C. IMPRESSUM
Version | 4.5 | 2020-06-24
Authors | Ward Goldthorpe (Sustainable Decisions Limited)
Lionel Avignon (Sustainable Decisions Limited)
Disclaimer | This tool is for informational purposes only. Sustainable Decisions Limited is not responsible and does not accept any liability whatsoever for the accuracy of this tool or any data within it.
This tool does not represent an endorsement by Sustainable Decisions Limited of any activity or project.
Licence | Sustainable Decisions Limited owns the copyright to this work and this tool is licenced to users under the Creative Commons licence: |  |  |  | CC BY-ND 4.0
Attribution | This tool is based on risk categories from the following public domain work under Creative Commons Licence: |  |  | CC BY-NC-SA 3.0
Climate Policy Initiative, 2013, Risk Gaps: A Map of Risk Mitigation Instruments for Clean Investments
http://climatepolicyinitiative.org/wp-content/uploads/2013/01/Risk-Gaps-A-Map-of-Risk-Mitigation-Instruments-for-Clean-Investments.pdf
Copyright © 2013 Climate Policy Initiative (CPI)
Changes have been made to the risk types, and risk mitigation measures and instruments.
Acknowledgment | ACT ELEGANCY, Project No 271498, has received funding from DETEC (CH), BMWi (DE), RVO (NL), Gassnova (NO), BEIS (UK), Gassco, Equinor and Total, and is cofunded by the European Commission under the Horizon 2020 programme, ACT Grant Agreement No 691712.

## Detailed Instructions
DETAILED INSTRUCTIONS
Overview Information | * Sheet "Overview Information * Firstly determine the business opportunities of relevance for the H2-CCS integrated chain of the case study to understand how many risk assessments need to be completed and fill in the table in the tab 'Overview Information'. | [5 empty] | §
* The user may decide to group business opportunities together to represent vertical integration of the value chain components in one entity, those which are/will be managd by the same entity (public/private) or where the business risks are fully integrated within the same entity. Up to 9 business groupings are possible and the user should enter a number for each grouping between 1 and 9. The cells are conditionally formatted to automatically fill them with colour based on these numbers for better visualisation of the groupings.
Top Table - Investment Barriers - Detailed Guidance | * From the risk assessement table (bottom table - see below), or from prior knowledge, identify the investment barriers for those risks with an investability rating of 5, i.e. the main facts/circumstances which drive the rating to be quantified as "5"
- Column A and B: identify and list the investment barriers (NB: Columns C to G and I to L do not apply to investment barriers).
- Column H: Copy from the previous risk assessment whether only the business opportunity is impacted or whether it is a system risk that affects the H2 chain, CCS chain or whole H2-CCS chain.
- Column M to O: propose mitigation measure(s) using a bow-tie approach and select relevant pre-defined categories. The categories are listed below with additional guidance and examples.
- Column P and Q: determine the current status of the measure (whether the measure is being developed or does not exist) and whether government intervention is required.
- Column R: estimate the investability rating of the identified business risks after the application of mitigation measures.
Bottom Table - Business Risks - Detailed Guidance | * For each of the selected market opportunities, use the attached template to:
- Column B: identify and list the main business risks relevant to the chosen business opportunity for each risk category
- Column C to G: assess the nature of their impact on the investment case by ticking any of the pre-defined five categories (cost, revenue, financing, schedule, liabilities).
- Column H: determine whether the risk affects only the business opportunity or whether it is a system risk that affects the H2 chain, CCS chain or whole H2-CCS chain.
- Column I and J: determine the business risk likelihood and impact ratings using the guidance tables below. The risk rating will be calculated as the product of these and returned in Column J.
- Column L: determine the investability rating from the chain perspective resulting from the impact of this business risk using the private or public sector investability rating guidance below.
- Column M to O: Define mitigation measure(s) using a bow-tie approach and select relevant pre-defined categories. The categories are listed below with additional guidance and examples.
- Column P and Q: determine the current status of the measure (whether the measure exists, is being developed or does not exist) and whether government intervention is required.
- Column R: estimate the investability rating of the identified business risks after the application of mitigation measures.
* General reminder help is provided in column header notes.
| ASSESSMENT METHODOLOGY |  | PRIVATE SECTOR INVESTABILITY RATING GUIDANCE |  | PUBLIC SECTOR INVESTABILITY RATING GUIDANCE
|  |  | Investability Rating | Guidance | Investability Rating | Guidance
|  |  | 1 | Established business opportunity with standard business risks. Investment open to standard market players with standard financing and insurance available | 1 | Established public sector investment activity and/or risk profile
|  |  | 2 | Medium risk investment with debt financing available at short tenor and high interest, higher than standard IRR required, risk profile acceptable to more than 50% of market players | 2 | Medium risk to Government, small number of previous public sector investments with similar risk profile, general community support for the activity, infrastructure, or service
|  |  | 3 | High risk investment with low debt ratio bank financing available, proven technology and acceptable regulatory and legal environment | 3 | High risk investment with potential for stranded or under-performing assets left in public sector hands
|  |  | 4 | Investment requires high risk appetite - First mover investor - No debt financing available, strategic investment, company with large balance sheet | 4 | Investment requires high risk appetite from Government with Treasury buy-in, very strong or new policy support, likely a need for new legislative mechanisms, possible need for bi-partisan agreement in parliament
|  |  | 5 | No Investment possible - uncapped or unmanageable liabilities, high uncertainty of revenue and cost, unacceptable performance guarantees and warranties | 5 | No public investment possible - political or financial exposure too high
| RISK MITIGATION MEASURE CATEGORY GUIDANCE |  | RISK LIKELIHOOD RATING GUIDANCE |  | RISK IMPACT RATING GUIDANCE
| Mitigation Measure Category | Guidance | Risk Likelihood | Guidance | Risk Impact | Guidance
| Contractual Terms | Examples include: take or pay, bank guarantees, pricing structure, change of control and change of law provisions, risk allocation, liability limits for specific events, consequential damages | 1 | Very unlikely | 1 | Insignificant
| Financial Market and Debt Instruments | Minimum repayment levels, debt service cover ratio, step in rights, swaps, derivative instruments, new technology guarantees/requirements | 2 | Unlikely | 2 | Minor
| Insurance | Insurance cover to protect against specific risks and cap liabilities | 3 | Possible | 3 | Moderate
| Technology | Improvements in technology to improve reliability, improve efficiency, reduce capex/opex, reduce uncertainty of unplanned operational events | 4 | Likely | 4 | Major
| Policy and Market Signals | Policy commitments, targets and carbon budgets, Principles for evaluating investment – (social economic benefits), decision-making structure | 5 | Very Likely | 5 | Severe
| Regulations, Legal and Influence | Legislative changes to define, allocate and reduce liabilities, legal requirements for permitting and planning consent including financial guarantees and liabiity for decommissioning, pollution…
| Financial Support | Financial support mechanisms (grants, tax allowances, FITs, subsidies, CfDs…), public sector underwriting, Third Party Access policy, Regulated/Unregulated business
| Market Design, Supervision, Market Provider | Intervention for competition, tradeable permits, competitive tendering, direct service or goods provision,
| Ownership Structure / Investor Type | Joint ventures, strategic partnerships and vertical integration of value chain, impact of government participation, public-private ownership/operating model
Business Risk
Investment Barriers
Consequences
Causes
Impact Mitigation
Likelihood Reduction

## Risk Categories
BUSINESS RISK CATEGORY | RISK TYPE | DESCRIPTION
Political, policy, and social risks These risks derive from both the legitimate actions of authorities exercising their legislative functions in the interest of the public (policy/regulatory risks), and illegitimate and discriminatory acts by authorities and citizens, and political violence and instability. | Regulatory | changes to standards, third party access regulations, etc
| Policy Change | changes to tariffs/subsidies or other commercial/financial incentives or failure to implement agreed tariff increases (to protect customers and avoid social unrest)
| Legal and Ownership rights | expropriation or nationalization of project assets, unreliability of legal system, etc
| Permitting and Consenting | delays, changes, unacceptable permit conditions, etc
| Reputation and Social | from opposition to project by private individuals to large communities to social unrest and political violence.
| Political and Governance | Political and Governance risks: corruption and bribery, procurement, discriminatory treatment, repeal of contracts, project cancellation, trapped in-country capital, etc
Technical and Physical risks These risks derive from the physical characteristics of the assets and/ or the surrounding environment. | Construction | cost overruns, delays, technology underperformance
| Operational | performance, reliability and availability,
| Output and Service Reliability | risk of product unavailability (H2 supply for H2 markets and therefore natural gas supply, CO2 supply for CO2 transportation and storage business)
| Environmental impact | unforeseen costs of operational compliance, clean up liabilities from incidents, etc
| Decommissioning | timing (earlier than anticipated), cost (higher costs than anticipated), reputation (public opposition), inability or delay to transfer storage site to competent authority
Market and Commercial Risks These risks derive from the action of markets and commercial counterparties, the economic value of the output (price, volume) and the financial dimension (cost and availability of capital, liquidity) | Currency and exchange | Currency and exchange risks
| Market Development/Demand (uncertainty of revenue) | uncertainty on volume, risks of infrastructure oversizing, uncertainty on market pricing (carbon pricing, commodity pricing, etc)
| Access to Capital | availability and cost of capital, term, liquidity for refinancing
| Counterparty | risk of default of contractual counterparties on payments and performance obligations
| Exit/Liquidity | Exit/Liquidity risks: inability to monetize investment value prior to the end of the life of the assets for equity and debt investors as well as public investors.
Outcome Risks These risks relate to the ability of the project(s) to deliver the desired outcomes for the public for a given budget | Emission Reduction | failure to deliver emission reduction expected prior to project execution OR emission reductions sufficient in comparison to competing technologies that have become available in parallel.
| Co-impact/ negative indirect Impact (social, health, economic benefits) | risks of under delivery of indirect outcomes such as social, health and economic benefits (employment, social regeneration, tax revenue, improved air quality, etc)
| Public Budget Impact | risks of cost overruns and financial resources required exceed budget available
| Asset underperformance/stranded asset ("white elephant") | risk of overall underperformance of asset in comparison to competing green technologies and over investment due to oversizing. Asset is “stranded”. Includes underperformance or lower capacity of geological storage site.

## Overview Information
KEY INFORMATION
Respondent Name
Respondent Sector
Project/Case Study Name
Project/Case Study Country
Business Opportunity under Assessment | CO2 Capture and Gathering
BUSINESS OPPORTUNITIES
# | H2-CCS Chain | Applicable (Y/N) | Grouping
1 | CO2 Storage |  | 1
2 | CO2 Transmission |  | 1
3 | CO2 Gathering |  | 2
4 | CO2 Capture |  | 2
5 | H2 Production
6 | H2 Transmission |  | 3
7 | H2 Storage |  | 3
# | H2 Distribution | Applicable (Y/N) | Grouping
8 | H2 medium pressure networks
9 | H2 low pressure networks |  | 4
10 | Road refuelling station distribution |  | 4
11 | Shipping
# | H2 Retail | Applicable (Y/N) | Grouping
12 | Large Stationary Power |  | 5
13 | Small Stationary Power |  | 6
14 | Mobility - Vehicles
15 | Mobility - Other
16 | Domestic Heat |  | 6
17 | Chemicals and Industry
18 | Power to X (Storage) |  | 5
Note on B3: Help: Please provide your name/name of your organisation
Note on B5: Help: Please provide the business sector your organisation primarily operates in
Note on B7: Help: Please provide the name of the case study to which this assessment applies
Note on B8: Help: Please provide the case study country / region / continent ...
Note on B9: Help: Please provide the selected business opportunity under assessment in this spreadsheet
Note on D13: Help: Select value chain components which are relevant to the case study or to a specific investability risk analysis
Note on E13: Help: Please group any value chain components which are/will be managd by the same entity (public/private) or where the investment risks are fully borne by the same entity by entering a number for thr grouping between 1 and 9. The cells are conditionally formatted to automatically colour them based on these numbers for better visualisation of the groupings.
Note on D22: Help: Select value chain components which are relevant to the case study or to a specific investability risk analysis
Note on E22: Help: Please colour code all cells of value chain components which are/will be managd by the same entity (public/private). These can be grouped to minimise business risk
Note on D28: Help: Select value chain components which are relevant to the case study or to a specific investability risk analysis
Note on E28: Help: Please colour code all cells of value chain components which are/will be managd by the same entity (public/private). These can be grouped to minimise business risk

## Political, Policy and Social
Business Opportunity under Assessment:
CO2 Capture and Gathering
Risk Category | Investment Barriers (investability Rating 5) | [5 empty] | Scope of Chain Impact |  |  |  |  | Proposed Measure | Target of Mitigation Measure: Cause or Consequence? | Category | Current Status of Mitigation Measure | Government Intervention Required (y/n) | Investability Rating (Post Mitigation)
Regulatory risk | Missing market for large scale hydrogen use | [5 empty] | H2-CCS Chain |  |  |  |  | Measure 1 | Control of Cause: Likelihood Reduction | Policy and Market Signals | Non-Existing | yes | 1
[12 empty] | Measure 2 | Recovery from Consequence: Impact Reduction | Regulations, Legal and Influence | Early stage of development | yes | 2
Risk Category | Business Risks | Nature of Impact |  |  |  |  | Scope of Chain Impact | Risk Quantification |  |  | Investability Rating | Mitigation Measures | Target of Mitigation Measure: Cause or Consequence? | Category | Current Status of Mitigation Measure | Government Intervention Required (y/n) | Investability Rating (Post Mitigation)
|  | Cost | Revenue | Financing | Schedule | Liabilities |  | Likelihood | Impact | Rating
REGULATORY | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
POLICY CHANGE | Risk 1 | ✘ | ✔ | ✘ | ✘ | ✔ | CCS Chain | 4 | 3 | 12 | 1 | Measure 1 | Control of Cause: Likelihood Reduction | Ownership Structure / Investor Type | Non-Existing | no | 1
| Risk 2 | ✘ | ✔ | ✘ | ✘ | ✘ | CCS Chain | 3 | 3 | 9 | 2 | Measure 2 | Recovery from Consequence: Impact Reduction | Insurance | Existing | no | 2
| Risk 3 | ✔ | ✔ | ✔ | ✘ | ✔ | H2-CCS Chain | 1 | 5 | 5 | 3 | Measure 3 | Recovery from Consequence: Impact Reduction | Insurance | Non-Existing | no | 3
LEGAL AND OWNERSHIP RIGHTS | Risk 1 | ✘ | ✔ | ✘ | ✘ | ✔ | CCS Chain | 4 | 3 | 12 | 1 | Measure 1 | Control of Cause: Likelihood Reduction | Ownership Structure / Investor Type | Non-Existing | no | 1
| Risk 2 | ✘ | ✔ | ✘ | ✘ | ✘ | CCS Chain | 3 | 3 | 9 | 2 | Measure 2 | Recovery from Consequence: Impact Reduction | Insurance | Existing | no | 2
| Risk 3 | ✔ | ✔ | ✔ | ✘ | ✔ | H2-CCS Chain | 1 | 5 | 5 | 3 | Measure 3 | Recovery from Consequence: Impact Reduction | Insurance | Non-Existing | no | 3
PERMITTING AND CONSENTING | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
REPUTATION AND SOCIAL | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
POLITICAL AND GOVERNANCE | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
Note on H3: Help: Determine whether the risk affects only the business opportunity or whether it is a system risk that affects the H2 chain, CCS chain or whole H2-CCS chain.
Note on M3: Help: Propose mitigation measure(s) using a bow-tie approach and select relevant pre-defined categories in column N.
Note on O3: Help: Select the pre-defined category for the mitigation measure. More detailed guidnace is provided in the instructions.
Note on P3: Help: Select the status of the mitigation measure. Take account of the fact that the measure may be a known or common measure in another sector or situation and could be applicable to this case. Alternatively it may be novel to the current circumstances and hence at an earlier stage of development.
Note on Q3: Help: Indicate if the mitigation measure requires government support or involvement.
Note on R3: Help: Select the investability rating from the 1-5 scales in the instructions depending on whether the assessment is from a public or private entity perspective.tainty of revenue and cost
Note on C10: Help: Consider the types of impact the investability barrier can have on a business case
Note on H10: Help: Determine whether the risk affects only the business opportunity or whether it is a system risk that affects the H2 chain, CCS chain or whole H2-CCS chain.
Note on I10: Help: Select the risk likelihood and impact from the 1-5 scales in the instructions. The rating is calculated as the rpoduct of the two.
Note on L10: Help: Select the investability rating from the 1-5 scales in the instructions depending on whether the assessment is from a public or private entity perspective.
Note on M10: Help: Propose mitigation measure(s) using a bow-tie approach and select relevant pre-defined categories in column N.
Note on O10: Help: Select the pre-defined category for the mitigation measure. More detailed guidnace is provided in the instructions.
Note on P10: Help: Select the status of the mitigation measure. Take account of the fact that the measure may be a known or common measure in another sector or situation and could be applicable to this case. Alternatively it may be novel to the current circumstances and hence at an earlier stage of development.
Note on Q10: Help: Indicate if the mitigation measure requires government support or involvement.
Note on R10: Help: Select the investability rating from the 1-5 scales in the instructions depending on whether the assessment is from a public or private entity perspective.tainty of revenue and cost

## Technical and Physical
Business Opportunity under Assessment:
CO2 Capture and Gathering
Risk Category | Investment Barriers (investability Rating 5) | [5 empty] | Scope of Chain Impact |  |  |  |  | Proposed Measure | Target of Mitigation Measure: Cause or Consequence? | Category | Current Status of Mitigation Measure | Government Intervention Required (y/n) | Investability Rating (Post Mitigation)
| Missing market for large scale hydrogen use | [5 empty] | H2-CCS Chain |  |  |  |  | Measure 1 | Control of Cause: Likelihood Reduction | Policy and Market Signals | Non-Existing | yes | 1
[12 empty] | Measure 2 | Recovery from Consequence: Impact Reduction | Regulations, Legal and Influence | Early stage of development | yes | 2
Risk Category | Business Risks | Nature of Impact |  |  |  |  | Scope of Chain Impact | Risk Quantification |  |  | Investability Rating | Mitigation Measures | Target of Mitigation Measure: Cause or Consequence? | Category | Current Status of Mitigation Measure | Government Intervention Required (y/n) | Investability Rating (Post Mitigation)
|  | Cost | Revenue | Financing | Schedule | Liabilities |  | Likelihood | Impact | Rating
CONSTRUCTION | Risk 1 | ✘ | ✔ | ✘ | ✘ | ✔ | CCS Chain | 4 | 3 | 12 | 1 | Measure 1 | Control of Cause: Likelihood Reduction | Ownership Structure / Investor Type | Non-Existing | no | 1
| Risk 2 | ✘ | ✔ | ✘ | ✘ | ✘ | CCS Chain | 3 | 3 | 9 | 2 | Measure 2 | Recovery from Consequence: Impact Reduction | Insurance | Existing | no | 2
| Risk 3 | ✔ | ✔ | ✔ | ✘ | ✔ | H2-CCS Chain | 1 | 5 | 5 | 3 | Measure 3 | Recovery from Consequence: Impact Reduction | Insurance | Non-Existing | no | 3
OPERATIONAL | Risk 1 | ✘ | ✔ | ✘ | ✘ | ✔ | CCS Chain | 4 | 3 | 12 | 1 | Measure 1 | Control of Cause: Likelihood Reduction | Ownership Structure / Investor Type | Non-Existing | no | 1
| Risk 2 | ✘ | ✔ | ✘ | ✘ | ✘ | CCS Chain | 3 | 3 | 9 | 2 | Measure 2 | Recovery from Consequence: Impact Reduction | Insurance | Existing | no | 2
| Risk 3 | ✔ | ✔ | ✔ | ✘ | ✔ | H2-CCS Chain | 1 | 5 | 5 | 3 | Measure 3 | Recovery from Consequence: Impact Reduction | Insurance | Non-Existing | no | 3
OUTPUT AND SERVICE RELIABILITY | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
ENVIRONMENTAL IMPACT | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
DECOMMISSIONING | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
Note on H3: Help: Determine whether the risk affects only the business opportunity or whether it is a system risk that affects the H2 chain, CCS chain or whole H2-CCS chain.
Note on M3: Help: Propose mitigation measure(s) using a bow-tie approach and select relevant pre-defined categories in column N.
Note on O3: Help: Select the pre-defined category for the mitigation measure. More detailed guidnace is provided in the instructions.
Note on P3: Help: Select the status of the mitigation measure. Take account of the fact that the measure may be a known or common measure in another sector or situation and could be applicable to this case. Alternatively it may be novel to the current circumstances and hence at an earlier stage of development.
Note on Q3: Help: Indicate if the mitigation measure requires government support or involvement.
Note on R3: Help: Select the investability rating from the 1-5 scales in the instructions depending on whether the assessment is from a public or private entity perspective.tainty of revenue and cost
Note on C10: Help: Consider the types of impact the investability barrier can have on a business case
Note on H10: Help: Determine whether the risk affects only the business opportunity or whether it is a system risk that affects the H2 chain, CCS chain or whole H2-CCS chain.
Note on I10: Help: Select the risk likelihood and impact from the 1-5 scales in the instructions. The rating is calculated as the rpoduct of the two.
Note on L10: Help: Select the investability rating from the 1-5 scales in the instructions depending on whether the assessment is from a public or private entity perspective.
Note on M10: Help: Propose mitigation measure(s) using a bow-tie approach and select relevant pre-defined categories in column N.
Note on O10: Help: Select the pre-defined category for the mitigation measure. More detailed guidnace is provided in the instructions.
Note on P10: Help: Select the status of the mitigation measure. Take account of the fact that the measure may be a known or common measure in another sector or situation and could be applicable to this case. Alternatively it may be novel to the current circumstances and hence at an earlier stage of development.
Note on Q10: Help: Indicate if the mitigation measure requires government support or involvement.
Note on R10: Help: Select the investability rating from the 1-5 scales in the instructions depending on whether the assessment is from a public or private entity perspective.tainty of revenue and cost

## Market and Commercial
Business Opportunity under Assessment:
CO2 Capture and Gathering
Risk Category | Investment Barriers (investability Rating 5) | [5 empty] | Scope of Chain Impact |  |  |  |  | Proposed Measure | Target of Mitigation Measure: Cause or Consequence? | Category | Current Status of Mitigation Measure | Government Intervention Required (y/n) | Investability Rating (Post Mitigation)
Market Development/Demand (uncertainty of revenue) | Missing market for large scale hydrogen use | [5 empty] | H2-CCS Chain |  |  |  |  | Measure 1 | Control of Cause: Likelihood Reduction | Policy and Market Signals | Non-Existing | yes | 1
[12 empty] | Measure 2 | Recovery from Consequence: Impact Reduction | Regulations, Legal and Influence | Early stage of development | yes | 2
Risk Category | Business Risks | Nature of Impact |  |  |  |  | Scope of Chain Impact | Risk Quantification |  |  | Investability Rating | Mitigation Measures | Target of Mitigation Measure: Cause or Consequence? | Category | Current Status of Mitigation Measure | Government Intervention Required (y/n) | Investability Rating (Post Mitigation)
|  | Cost | Revenue | Financing | Schedule | Liabilities |  | Likelihood | Impact | Rating
CURRENCY AND EXCHANGE | Risk 1 | ✘ | ✔ | ✘ | ✘ | ✔ | CCS Chain | 4 | 3 | 12 | 1 | Measure 1 | Control of Cause: Likelihood Reduction | Ownership Structure / Investor Type | Non-Existing | no | 1
| Risk 2 | ✘ | ✔ | ✘ | ✘ | ✘ | CCS Chain | 3 | 3 | 9 | 2 | Measure 2 | Recovery from Consequence: Impact Reduction | Insurance | Existing | no | 2
| Risk 3 | ✔ | ✔ | ✔ | ✘ | ✔ | H2-CCS Chain | 1 | 5 | 5 | 3 | Measure 3 | Recovery from Consequence: Impact Reduction | Insurance | Non-Existing | no | 3
MARKET DEVELOPMENT AND DEMAND RISKS | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
ACCESS TO CAPITAL | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
COUNTERPARTY | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
EXIT/LIQUIDITY/ REFINANCING RISKS | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
Note on H3: Help: Determine whether the risk affects only the business opportunity or whether it is a system risk that affects the H2 chain, CCS chain or whole H2-CCS chain.
Note on M3: Help: Propose mitigation measure(s) using a bow-tie approach and select relevant pre-defined categories in column N.
Note on O3: Help: Select the pre-defined category for the mitigation measure. More detailed guidnace is provided in the instructions.
Note on P3: Help: Select the status of the mitigation measure. Take account of the fact that the measure may be a known or common measure in another sector or situation and could be applicable to this case. Alternatively it may be novel to the current circumstances and hence at an earlier stage of development.
Note on Q3: Help: Indicate if the mitigation measure requires government support or involvement.
Note on R3: Help: Select the investability rating from the 1-5 scales in the instructions depending on whether the assessment is from a public or private entity perspective.tainty of revenue and cost
Note on C10: Help: Consider the types of impact the investability barrier can have on a business case
Note on H10: Help: Determine whether the risk affects only the business opportunity or whether it is a system risk that affects the H2 chain, CCS chain or whole H2-CCS chain.
Note on I10: Help: Select the risk likelihood and impact from the 1-5 scales in the instructions. The rating is calculated as the rpoduct of the two.
Note on L10: Help: Select the investability rating from the 1-5 scales in the instructions depending on whether the assessment is from a public or private entity perspective.
Note on M10: Help: Propose mitigation measure(s) using a bow-tie approach and select relevant pre-defined categories in column N.
Note on O10: Help: Select the pre-defined category for the mitigation measure. More detailed guidnace is provided in the instructions.
Note on P10: Help: Select the status of the mitigation measure. Take account of the fact that the measure may be a known or common measure in another sector or situation and could be applicable to this case. Alternatively it may be novel to the current circumstances and hence at an earlier stage of development.
Note on Q10: Help: Indicate if the mitigation measure requires government support or involvement.
Note on R10: Help: Select the investability rating from the 1-5 scales in the instructions depending on whether the assessment is from a public or private entity perspective.tainty of revenue and cost

## Outcome
Business Opportunity under Assessment:
CO2 Capture and Gathering
Risk Category | Investment Barriers (investability Rating 5) | [5 empty] | Scope of Chain Impact |  |  |  |  | Proposed Measure | Target of Mitigation Measure: Cause or Consequence? | Category | Current Status of Mitigation Measure | Government Intervention Required (y/n) | Investability Rating (Post Mitigation)
| Missing market for large scale hydrogen use | [5 empty] | H2-CCS Chain |  |  |  |  | Measure 1 | Control of Cause: Likelihood Reduction | Policy and Market Signals | Non-Existing | yes | 1
[12 empty] | Measure 2 | Recovery from Consequence: Impact Reduction | Regulations, Legal and Influence | Early stage of development | yes | 2
Risk Category | Business Risks | Nature of Impact |  |  |  |  | Scope of Chain Impact | Risk Quantification |  |  | Investability Rating | Mitigation Measures | Target of Mitigation Measure: Cause or Consequence? | Category | Current Status of Mitigation Measure | Government Intervention Required (y/n) | Investability Rating (Post Mitigation)
|  | Cost | Revenue | Financing | Schedule | Liabilities |  | Likelihood | Impact | Rating
EMISSION REDUCTION | Risk 1 | ✘ | ✔ | ✘ | ✘ | ✔ | CCS Chain | 4 | 3 | 12 | 1 | Measure 1 | Control of Cause: Likelihood Reduction | Ownership Structure / Investor Type | Non-Existing | no | 1
| Risk 2 | ✘ | ✔ | ✘ | ✘ | ✘ | CCS Chain | 3 | 3 | 9 | 2 | Measure 2 | Recovery from Consequence: Impact Reduction | Insurance | Existing | no | 2
| Risk 3 | ✔ | ✔ | ✔ | ✘ | ✔ | H2-CCS Chain | 1 | 5 | 5 | 3 | Measure 3 | Recovery from Consequence: Impact Reduction | Insurance | Non-Existing | no | 3
NEGATIVE DIRECT IMPACT (SOCIAL, HEALTH, ECONOMIC, etc. | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
PUBLIC BUDGET | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
ASSET UNDERPERFORMANCE/ STRANDED ASSET | [9 empty] | 0 | 4 | [5 empty] | 4
[10 empty] | 0 | 5 | [5 empty] | 5
0
Note on H3: Help: Determine whether the risk affects only the business opportunity or whether it is a system risk that affects the H2 chain, CCS chain or whole H2-CCS chain.
Note on M3: Help: Propose mitigation measure(s) using a bow-tie approach and select relevant pre-defined categories in column N.
Note on O3: Help: Select the pre-defined category for the mitigation measure. More detailed guidnace is provided in the instructions.
Note on P3: Help: Select the status of the mitigation measure. Take account of the fact that the measure may be a known or common measure in another sector or situation and could be applicable to this case. Alternatively it may be novel to the current circumstances and hence at an earlier stage of development.
Note on Q3: Help: Indicate if the mitigation measure requires government support or involvement.
Note on R3: Help: Select the investability rating from the 1-5 scales in the instructions depending on whether the assessment is from a public or private entity perspective.tainty of revenue and cost
Note on C10: Help: Consider the types of impact the investability barrier can have on a business case
Note on H10: Help: Determine whether the risk affects only the business opportunity or whether it is a system risk that affects the H2 chain, CCS chain or whole H2-CCS chain.
Note on I10: Help: Select the risk likelihood and impact from the 1-5 scales in the instructions. The rating is calculated as the rpoduct of the two.
Note on L10: Help: Select the investability rating from the 1-5 scales in the instructions depending on whether the assessment is from a public or private entity perspective.
Note on M10: Help: Propose mitigation measure(s) using a bow-tie approach and select relevant pre-defined categories in column N.
Note on O10: Help: Select the pre-defined category for the mitigation measure. More detailed guidnace is provided in the instructions.
Note on P10: Help: Select the status of the mitigation measure. Take account of the fact that the measure may be a known or common measure in another sector or situation and could be applicable to this case. Alternatively it may be novel to the current circumstances and hence at an earlier stage of development.
Note on Q10: Help: Indicate if the mitigation measure requires government support or involvement.
Note on R10: Help: Select the investability rating from the 1-5 scales in the instructions depending on whether the assessment is from a public or private entity perspective.tainty of revenue and cost

## Drop Down Lists (hidden)
Category | System Level Impact | Impact on Investability | Government Intervention |  | Current Status | Mitigation Target | Investability Rating | Investability Rating Definitions
Contractual | Individual | Low | yes | ✔ | Existing | Control of Cause: Likelihood Reduction | 1 | Private Sector:
Financial Markets and Debt Instruments | H2 Chain | Medium | no | ✘ | Late stage of development | Recovery from Consequence: Impact Reduction | 2 | 1 - Established Business Risks
Insurance | CCS Chain | High |  |  | Early stage of development |  | 3 | 2 - Medium Risk - debt financing available
Technology | H2-CCS Chain |  |  |  | Non-Existing |  | 4 | 3 - High risk - low ratio debt financing
Policy and Market Signals | [6 empty] | 5 | 4 - High risk appetite - No debt financing available, strategic investment, large balance sheet
Regulations, Legal and Influence | [7 empty] | 5 - No private investment possible
Financial Support | [7 empty] | Public Sector:
Market Design, Supervision, Market Provider | [7 empty] | 1 - Established Business Risks
Ownership Structure / Investor Type | [7 empty] | 2 - Medium Risk - small number of investment precedents
3 - High risk - potential for stranded public assets
4 - High risk appetite - legislative or Treasury support
5 - No public investment possible